## Slide 1
AUDIT READINESS + CONTROL IMPROVEMENT
Strengthening branch audit readiness through daily controls
Guaranty Trust Bank (GTBank) | Customer Relationship Manager
2018–2020 portfolio case study
65%
baseline audit score
95%
final audit score
Agnes Iwaye | Project Management Portfolio

## Slide 2
A failed audit exposed a recurring control-readiness gap
02
The branch was correcting documentation and transaction issues too late—often during pre-audit preparation—creating repeat findings, unclear ownership and avoidable fraud or compliance exposure.
STARTING POINT
≈65% audit score
Previous pass performance generally ≤75%
PROJECT OBJECTIVE
Build continuous audit readiness and reach approximately 95% performance
My role
• Planned pre-audit readiness and coordinated evidence
• Introduced a daily call-over control
• Assigned exceptions to accountable process owners
• Tracked closure and escalated aging or high-risk issues
Control environment
Operations • Internal Control • Tellers / Cash Office
Fraud & AML • Cybersecurity • Relationship Managers
Branch leadership • External auditors

## Slide 3
Daily call-over turned audit preparation into a continuous control
03
01
REVIEW
Check daily transaction batches, approvals and supporting documents.
02
LOG
Record omissions, posting errors, KYC gaps and control exceptions.
03
ASSIGN
Route actions to operations, tellers, AML, cybersecurity or internal control.
04
VERIFY
Confirm corrections and retain closure evidence in the issue register.
05
ESCALATE
Raise high-risk, repeat or overdue items to branch leadership.
Management effect
Exceptions became visible while they were still correctable—before they accumulated into formal audit findings.

## Slide 4
Clear ownership connected frontline operations to independent assurance
04
FRONTLINE
Tellers / Cash Office
Operations
Relationship Managers
CONTROL OWNERS
Customer Relationship Manager
Branch Manager
Internal Control
RISK + SECURITY
Fraud & AML
Cybersecurity
Compliance support
ASSURANCE
Internal Audit
External Auditors
Executive reporting
Communication rhythm
Daily exception huddle
Weekly readiness review
Monthly risk review
Pre-audit evidence checkpoint
Escalation triggers: high-risk exception • overdue corrective action • repeat finding • readiness below 90%

## Slide 5
Audit performance reached 95% as exceptions declined
05
Chart: 
| 2018 baseline | 2019 H1 | 2019 year-end | 2020 year-end
Audit performance | 65 | 80 | 88 | 95
Exception index | 100 | 90 | 80 | 70
OUTCOME
+30 percentage points
CONTROL QUALITY
30% fewer errors / exceptions
EVIDENCE NOTE
Intermediate review-point values are illustrative; 65%, 95% and the 30% reduction are user-provided.

## Slide 6
The project improved readiness, control discipline and evidence quality
06
95%
final audit performance
+30 pts
improvement from baseline
−30%
documentation / transaction errors
145K
transactions within modeled audit scope
What changed operationally
Daily control replaced last-minute audit clean-up
Exceptions had named owners and closure dates
High-risk issues reached AML, fraud or cybersecurity faster
Evidence packages became easier to validate before audit arrival

## Slide 7
Daily controls addressed the causes of weak audits
07
Observed risk | Daily control | Primary owner | Evidence retained
Missing or incomplete documents | Same-day document call-over | CRM + Operations | Corrected form / approval
Posting or transaction mismatch | Batch reconciliation and exception log | Operations + Tellers | Correction reference
Fraud / AML indicator | Risk classification and rapid escalation | Fraud & AML | Review decision / case note
Access-control exception | Escalation to cybersecurity | Cybersecurity | Access review / remediation
Repeat or overdue finding | Aging report and branch-manager escalation | Branch Manager + Internal Control | Closure evidence / sign-off
Control principle: correct exceptions at the point of work, preserve evidence and escalate based on risk—not proximity to the audit date.

## Slide 8
The branch moved from diagnosis to sustained readiness
08
2018
DIAGNOSE
Reviewed the failed audit result and identified recurring documentation, posting and ownership gaps.
2019 H1
IMPLEMENT
Introduced daily call-over, exception logging and assigned corrective actions.
2019 year-end
STANDARDIZE
Established weekly readiness reviews, evidence retention and cross-functional escalation.
2020 year-end
SUSTAIN
Embedded the control rhythm and achieved approximately 95% audit performance.
Modeled chronology: the precise number and dates of audit checkpoints should be validated before external publication.

## Slide 9
This project demonstrates project management through operational control
10
PLAN
Audit calendar
Readiness criteria
Risk-based priorities
COORDINATE
Cross-functional RACI
Communication cadence
Escalation paths
CONTROL
Daily call-over
Issue register
Closure evidence
IMPROVE
KPI tracking
Lessons learned
Sustained discipline
Portfolio positioning
A branch-level audit-readiness project that converted a failed control environment into a repeatable operating process, improved audit performance and reduced exceptions.
Evidence discipline: 65% baseline, 95% final and 30% error reduction are user-provided. Modeled volumes and intermediate review points remain illustrative.